## Project Estimation
Module | Description | Estimated Hours
Project Setup | Create and configure a new project structure using Angular. | 25
Setup environment configurations for dev, staging, and production.
Implement route guards for authentication and access control.
Define base routes for all modules (Home, Categories, Product Details, etc.).
Add interceptors for token handling, error interception, and API request logging.
Develop shared UI components such as Header (Navbar), Sidebar (Sidenav), and Footer.
Integrate a responsive layout grid to support all device sizes.
Global loader/spinner for API calls and lazy-loaded routes.
Centralized error handling service.
Define global styles, typography, and reusable SCSS variables.
Test and ensure responsiveness across mobile, tablet, and desktop.
Setup Git repository, ESLint/Prettier configurations, and basic CI setup if applicable.
Home Page | Develop responsive banner/hero section. | 15
Add navigation links and key CTA (Call-To-Action) sections.
Display featured products, offers, or categories using API data.
Implement carousel or slider for promotional items.
Connect API endpoints for dynamic data loading.
Card components for displaying items (used later in Categories/Product pages).
Ensure cross-browser compatibility and mobile responsiveness.
Categories Page | Grid-based responsive layout for displaying categories. | 12
Fetch and display categories from backend services.
Basic filter or sort by name, type, or popularity (if required).
Category card component for uniform display.
Link each category to corresponding product listings.
Optimize UI for mobile and tablet viewports.
Product Details Page | Product image carousel, title, price, and description. | 18
Specifications, reviews, and additional details.
Fetch detailed data via product ID.
Handle loading and error states gracefully.
Add “Add to Cart” or “Book Now” buttons.
Include recommended products section.
Fully responsive design ensuring optimal display for all devices.
This page includes payment integration for the Buy Now option.
Verify all data bindings and API connections.
| Total | 70